## Krishnan Moni Project Plan
Task Name | Start Date | End Date | Duration (Days)
Project Planning | 2018-06-01 | 2018-06-11 | 10
Write-Up - Project Title / Problem Statement / Objective | 2018-06-12 | 2018-06-14 | 2
Write-Up - Introduction | 2018-06-15 | 2018-06-25 | 10
Write-Up - General Literature Review | 2018-06-26 | 2018-07-01 | 5
Write-Up - Specific Literature Review (ED regulations) | 2018-07-02 | 2018-07-12 | 10
Write-Up - Specific Literature Review (Modeling methods) | 2018-07-13 | 2018-07-23 | 10
Write-UP - BBNs & IDs | 2018-07-24 | 2018-07-31 | 7
Learning Netica software | 2018-08-01 | 2018-08-11 | 10
Implementing ID Model in Netica | 2018-08-12 | 2018-08-22 | 10
Write-Up - ID model in Netica | 2018-08-23 | 2018-08-30 | 7
Write-Up - Results discussion | 2018-08-31 | 2018-09-05 | 5
Write-Up - Conclusion / Recommendation | 2018-09-06 | 2018-09-11 | 5
Appendices | 2018-09-12 | 2018-09-15 | 3
References | 2018-09-16 | 2018-09-20 | 4
Cover Page/Abstract/Table of Contents/Acknowledgements, etc | 2018-09-21 | 2018-09-23 | 2
Proofreading / Editing / Final changes | 2018-09-24 | 2018-09-27 | 3
Project Diary | 2018-06-01 | 2018-09-27 | 118